## Gantt Chart
Proyecto PrevenTech | [5 empty] | Gantt Chart Template © 2020 by Vertex42.com
Condominio El Descanso |  |  |  | Inicio del proyecto: | 2026-03-11
Sistema de Gestión de Mantenimiento Preventivo |  |  |  | Semana para mostrar: | 1 | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27
 | time axis 2026-03-09 to 2026-05-03
TAREA | ASIGNADO A | PROGRESO | INICIO | DÍAS | FIN | time axis 2026-03-09 to 2026-05-03
Análisis y Planificación |  | 100%
Identificación del problema | Lesly Díaz | 100% | 2026-03-11 | 4 | 2026-03-14
Reunión con cliente | Equipo completo | 100% | 2026-03-15 | 1 | 2026-03-15
Recopilación de información | Equipo completo | 100% | 2026-03-16 | 1 | 2026-03-16
Definición de objetivos y alcance | Equipo completo | 100% | 2026-03-17 | 1 | 2026-03-17
Definición de arquitectura | Ruth Gonzalez | 100% | 2026-03-18 | 1 | 2026-03-18
Levantamiento requerimientos funcionales | Maira Vidal | 100% | 2026-03-19 | 1 | 2026-03-19
Levantamiento requerimientos no funcionales | Lesly Díaz | 100% | 2026-03-20 | 1 | 2026-03-20
Definición de la metodología | Equipo completo | 100% | 2026-03-20 | 2 | 2026-03-21
Creación del repositorio en GitHub | Equipo completo | 100% | 2026-03-21 | 1 | 2026-03-21
Elaboración del Modelo Entidad-Relación (MER) | Lesly Díaz | 100% | 2026-03-22 | 2 | 2026-03-23
Elaboración de la Carta Gantt | Equipo completo | 100% | 2026-03-24 | 2 | 2026-03-25
Elaboración de la planilla de riesgos | Lesly Díaz | 100% | 2026-03-26 | 1 | 2026-03-26
Elaboración de la hoja de ruta del proyecto | Lesly Díaz | 100% | 2026-03-27 | 1 | 2026-03-27
Identificación de microservicios | Maira Vidal | 100% | 2026-03-27 | 1 | 2026-03-27
Diagrama de actividad | Lesly Díaz | 100% | 2026-03-27 | 2 | 2026-03-28
Diagrama de casos de uso | Ruth Gonzalez | 100% | 2026-03-28 | 1 | 2026-03-28
Diagrama de clases | Lesly Díaz | 100% | 2026-03-28 | 2 | 2026-03-29
Diagrama de componentes | Maira Vidal | 100% | 2026-03-29 | 1 | 2026-03-29
Diagrama de comunicación | Ruth Gonzalez | 100% | 2026-03-29 | 2 | 2026-03-30
Diagrama de despliegue | Lesly Díaz | 100% | 2026-03-30 | 1 | 2026-03-30
Diagrama de paquetes | Maira Vidal | 100% | 2026-03-30 | 1 | 2026-03-30
Diagrama de secuencia | Ruth Gonzalez | 100% | 2026-03-30 | 2 | 2026-03-31
Mockup en Canva | Equipo completo | 100% | 2026-03-31 | 1 | 2026-03-31
Diseño y Desarrollo |  | 0%
Configuración del entorno de desarrollo | Equipo completo | 0% | 2026-04-01 | 2 | 2026-04-02
Planificación técnica del desarrollo | Equipo completo | 0% | 2026-04-03 | 2 | 2026-04-04
Diseño físico de la base de datos en MySQL | Ruth González | 0% | 2026-04-05 | 3 | 2026-04-07
Creación del proyecto Backend en Spring Boot | Lesly Díaz | 0% | 2026-04-08 | 3 | 2026-04-10
Configuración del entorno Frontend en React | Maira Vidal | 0% | 2026-04-11 | 3 | 2026-04-13
Implementación de la base de datos | Lesly Díaz | 0% | 2026-04-14 | 3 | 2026-04-16
Desarrollo del microservicio de autenticación | Maira Vidal | 0% | 2026-04-17 | 3 | 2026-04-19
Desarrollo de interfaces de usuario | Ruth González | 0% | 2026-04-20 | 3 | 2026-04-22
Configuración de la conexión Backend–Base de Datos | Lesly Díaz | 0% | 2026-04-23 | 3 | 2026-04-25
Desarrollo del microservicio principal | Maira Vidal | 0% | 2026-04-26 | 5 | 2026-04-30
Implementación de componentes y navegación | Ruth González | 0% | 2026-05-01 | 4 | 2026-05-04
Implementación de APIs REST | Lesly Díaz | 0% | 2026-05-05 | 4 | 2026-05-08
Gestión y versionado del repositorio | Maira Vidal | 0% | 2026-05-09 | 4 | 2026-05-12
Integración del Frontend con el Backend | Ruth González | 0% | 2026-05-13 | 5 | 2026-05-17
Integración general del sistema | Equipo completo | 0% | 2026-05-18 | 5 | 2026-05-22
Documentación técnica del sistema | Equipo completo | 0% | 2026-05-23 | 5 | 2026-05-27
Pruebas y Validación |  | 0%
Planificación de las pruebas | Equipo completo | 0% | 2026-05-28 | 2 | 2026-05-29
Elaboración de casos de prueba | Equipo completo | 0% | 2026-05-30 | 2 | 2026-05-31
Preparación del entorno de pruebas | Lesly Díaz | 0% | 2026-06-01 | 2 | 2026-06-02
Ejecución de pruebas unitarias de la base de datos | Lesly Díaz | 0% | 2026-06-03 | 2 | 2026-06-04
Pruebas unitarias del Backend | Maira Vidal | 0% | 2026-06-05 | 2 | 2026-06-06
Pruebas unitarias del Frontend | Ruth González | 0% | 2026-06-07 | 2 | 2026-06-08
Pruebas de integración del Backend | Maira Vidal | 0% | 2026-06-09 | 2 | 2026-06-10
Pruebas de integración del Frontend | Ruth González | 0% | 2026-06-11 | 2 | 2026-06-12
Pruebas de integración con la base de datos | Lesly Díaz | 0% | 2026-06-13 | 2 | 2026-06-14
Pruebas funcionales del sistema | Equipo completo | 0% | 2026-06-15 | 2 | 2026-06-16
Pruebas de usabilidad | Ruth González | 0% | 2026-06-17 | 2 | 2026-06-18
Identificación y registro de errores | Maira Vidal | 0% | 2026-06-19 | 2 | 2026-06-20
Corrección de errores del Backend | Equipo completo | 0% | 2026-06-21 | 2 | 2026-06-22
Corrección de errores del Frontend y validación final | Equipo completo | 0% | 2026-06-23 | 2 | 2026-06-24
Presentación Final |  | 0%
Elaboración del informe final | Lesly Díaz | 0% | 2026-06-25 | 6 | 2026-06-30
Preparación de la demostración del sistema | Maira Vidal | 0% | 2026-07-01 | 5 | 2026-07-05
Diseño de la presentación y diapositivas | Ruth González | 0% | 2026-07-06 | 5 | 2026-07-10
Ensayo general de la exposición | Equipo completo | 0% | 2026-07-11 | 3 | 2026-07-13
Presentación final del proyecto | Equipo completo | 0% | 2026-07-14 | 1 | 2026-07-14

## Help (hidden)
Help
Instead of detailed help worksheet, please do the following if you have questions about how this spreadsheet works, or how to use this spreadsheet.
1) Watch the Video Tutorial on YouTube
https://youtu.be/8eKk0M2zGIk
2) Read the Following Page
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Although the content on the above page was created originally for the Excel template, most of the information about the use of formulas and ways to customize the Gantt chart apply just as well to the Google Sheets version.
Formula for % Complete of a summary task, based on its sub tasks:
SUMPRODUCT(days_range,percent_complete_range)/SUM(days_range)
To show the % Complete within the bars in the Gantt chart:
Select a cell within the Gantt chart area and go to Format > Conditional Formatting, then "turn on" the grey bar rule by changing 1=0 to 1=1 within the AND function.

## TermsOfUse (hidden)
Simple Gantt Chart for Google Sheets
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2020 Vertex42 LLC. All rights reserved.
This template is a copyrighted work under the Unites States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
The Share Settings for this spreadsheet must always be set to "Private"
Limited Private Sharing and Other Allowed Uses
See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html

## GanttChartPro (hidden)
Gantt Chart Template Pro for Google Sheets
Gantt Chart Template Pro, by Vertex42.com, is a spreadsheet template designed originally for Microsoft Excel that offers more features than the free version. When you purchase it, you will also get a link to download the Pro version for Google Sheets!!
Learn More About Gantt Chart Template Pro
- Visit the web page above to view screenshots and watch demo videos
Features in the Pro version for Google Sheets
Define task durations by specifying the number of Work Days
- In this free version, the inputs to define a task are the Start Date and the Calendar Day duration. In the Pro version, the default option is to enter the Start Date and the number of Work Days.
Choose whether to define task durations using Calendar Days or Work Days or End Dates
- The Pro version includes a larger set of template rows that provide more options for defining the Start date, End date, duration, and dependency of tasks.
Exclude holidays from work days
- List holidays and other non-working days in a separate sheet. When defining task durations using Work Days, these dates will be excluded.
Define what you mean by "Weekend" when using Work Days
- The Pro version allows you to define exactly which day(s) of the week you want to use as your weekend. The default is Saturday and Sunday.
Color-Code bars in the Gantt chart
- The Pro version includes a column for entering a color code like "k", "r", or "y" to change the color of the bars in the Gantt chart. The Help worksheet explains some advanced formulas that you could use in the Color column to automatically color a bar based on the name in the Lead column.
Define tasks dependences by specifying the predecessor WBS
- The template rows include an option for entering a Predecessor WBS. The Start date will be calculated as the day following the End date of the predecessor.